## Slide 1: Center for Vision (CVN) on Block 33 Move Planning & Logistics Timeline
Today
Activation of Move Team
January 2
Preliminary Move List Matrix Deadline
March 5
Aug ##
Nov 7
Dec 20
6 days
Formation and Activation of Bldg Gov Committees
January
18 days
Current Site Prelim Surveys
& Jobwalk Tours for Move Companies
February
24 days
Transition Planning for Daily Operations
Jun - Aug
16 days
Q4 2019 Phase 1 Move-in
Oct - Dec
25 days
March 15
Building Town Hall Meeting #2
Nov ##
2020
2019
Telephone & IT Device Detail on Move Matrix Deadline
June 5
Seat Assignments on Move Matrix Deadline
Change Management Activities for Open Plan Shared Resources
Jun - Aug
Move Logistics Instructional Town Hall Meeting #1
Sept ##
Building Town Hall Meeting #1
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Q1 2020 Phase 2 Move-in
Jan - Mar
Move Logistics Instructional Town Hall Meeting #2
Dec ##
Move-in Support
& Follow Up
Apr
Mar – Aug
Document Management Strategies for Moving to Paper-Lite
Draft Document Management Project Plan and Estimate Forms
Feb 1